## RJKIP_ACIU
Rani Jamara Kuleria Irrigation Project
Agricultural Component Implementation Unit (ACIU),
Tikapur, Kailali
(IDA credit No.6194-NP, Project ID No. P158364)
Annual Plan of Action for ACIU Approved Activities (FY 2018/19)
(NPR 00000)
Activity No. | S.No | Activities/Sub activities | Unit | Annual Target |  |  |  |  | Responsibility | Months | [47 empty] | Remarks
[10 empty] | July-Aug |  |  |  | Agu-Sep |  |  |  | Sep-Oct |  |  |  | Oct-Nov |  |  |  | Nov- Dec |  |  |  | Dec- Jan |  |  |  | Jan-Feb |  |  |  | Feb- Mar |  |  |  | Mar-Aprl |  |  |  | Aprl-May |  |  |  | May-June |  |  |  | June-July
|  |  |  | Annual | Budget | 1st | 2nd | 3rd |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
8.2.2.420 | 1 | Building construction of ACIU- office, Tikapur | No | 1 | 140 | 1 |  |  | DOA/ACIU
| 1.1 | Draft Bidding Documents (RFB) | bar: Agu-Sep 4 to Sep-Oct 2
| 1.2 | Specific procurement Notice | bar: Sep-Oct 3
| 1.3 | Amendments to Bidding Documents | bar: Sep-Oct 3
| 1.4 | Technical Bid Submission/Opening/minutes | bar: Sep-Oct 4 to Oct-Nov 4
| 1.5 | Evaluation of Technical proposal | bar: Oct-Nov 4
| 1.6 | Opening of Financial proposal/minutes | bar: Oct-Nov 4
| 1.7 | Bid validity Extension | bar: Oct-Nov 4
| 1.8 | Bid Evaluation Report and Recommendation for Award | bar: Nov- Dec 1
| 1.9 | Standstill/Derifing | bar: Nov- Dec 1
| 1.1 | Notification of Award | bar: Nov- Dec 2
| 1.11 | Signed contract | bar: Nov- Dec 2
| 1.12 | Contract Amendments | bar: Nov- Dec 2 to Mar-Aprl 2
| 1.13 | Contract completion | bar: Mar-Aprl 3 to June-July 2
| 1.14 | Contract Termination | bar: June-July 3 to June-July 4
8.2.2.421 | 2 | Construction of 4-wheel motor garej for ACIU Office, Tikapur | No | 1 | 15 |  | 1 |  | DOA/ACIU
| 2.1 | Draft Bidding Documents (RFSQ) | bar: Sep-Oct 2 to Sep-Oct 3
| 2.2 | Specific procurement Notice | bar: Sep-Oct 4
| 2.3 | Amendments to Bidding Documents | bar: Sep-Oct 4
| 2.4 | Technical Bid Submission/Opening/minutes | bar: Oct-Nov 1 to Oct-Nov 4
| 2.5 | Evaluation of Technical proposal | bar: Nov- Dec 1
| 2.6 | Opening of Financial proposal/minutes | bar: Nov- Dec 1
| 2.7 | Bid validity Extension | bar: Nov- Dec 1
| 2.8 | Bid Evaluation Report and Recommendation for Awar | bar: Nov- Dec 2
| 2.9 | Standstill/Derifing | bar: Nov- Dec 2
| 2.1 | Notification of Award | bar: Nov- Dec 3
| 2.11 | Signed contract | bar: Nov- Dec 3
| 2.12 | Contract Amendments | bar: Nov- Dec 4 to June-July 4
| 2.13 | Contract completion | bar: June-July 1 to June-July 4
| 2.14 | Contract Termination
8.4.4.12 | 3 | Procurement of Moterbikes | No | 6 | 12 | 6 |  |  | DOA/ACIU
| 3.1 | Draft Pre-qualification/Initial selection Documents | bar: Agu-Sep 4 to Sep-Oct 2
| 3.2 | Specific procurement Notice | bar: Sep-Oct 3
| 3.3 | Amendments to Pre qualification/ Initial selection doc | bar: Sep-Oct 3
| 3.4 | Opening/minutes of Pre qualification/Initial selection | bar: Sep-Oct 4 to Oct-Nov 4
| 3.5 | Pre qualification/Initial selection Evaluation Report | bar: Oct-Nov 4
| 3.6 | Draft Bidding Documents | bar: Oct-Nov 4 to Nov- Dec 2
| 3.7 | Amendments to Bidding Documents | bar: Nov- Dec 3
| 3.8 | Bid Submission/Opening/minutes | bar: Nov- Dec 3
| 3.9 | Bid validity Extension | bar: Nov- Dec 4 to Dec- Jan 4
| 3.1 | Bid Evaluation Report and Recommendation for Award | bar: Dec- Jan 4
| 3.11 | Standstill/Derifing | bar: Dec- Jan 4
| 3.12 | Notification of Award | bar: Dec- Jan 4
| 3.13 | Signed contract | bar: Jan-Feb 1
| 3.14 | Contract Amendments | bar: Jan-Feb 1
| 3.15 | Contract completion | bar: Jan-Feb 2
| 3.16 | Contract Termination | bar: Jan-Feb 2
8.5.1.1 | 4 | Procurement of Laptop computer | No | 2 | 3 | 2 |  |  | DOA/ACIU
| 4.1 | Draft Request for Quotation | bar: Sep-Oct 1 to Sep-Oct 3
| 4.2 | Specific procurement Notice | bar: Sep-Oct 4
| 4.3 | Invitation to Supplier/Contrator | bar: Sep-Oct 4
| 4.4 | Receive Quotations | bar: Oct-Nov 1 to Nov- Dec 1
| 4.5 | Comparision Quotations | bar: Nov- Dec 1
| 4.6 | Notification of Award | bar: Nov- Dec 1 to Nov- Dec 3
| 4.7 | Signed contract | bar: Nov- Dec 4
| 4.8 | Contract Amendments | bar: Nov- Dec 4
| 4.9 | Contract completion | bar: Dec- Jan 1
| 4.1 | Contract Termination
8.5.1.9 | 5 | Procurement of Desktop computer | No | 2 | 2 | 2 |  |  | DOA/ACIU
| 5.1 | Draft Request for Quotation | bar: Sep-Oct 1 to Sep-Oct 3
| 5.2 | Specific procurement Notice | bar: Sep-Oct 4
| 5.3 | Invitation to Supplier/Contrator | bar: Sep-Oct 4
| 5.4 | Receive Quotations | bar: Oct-Nov 1 to Nov- Dec 1
| 5.5 | Comparision Quotations | bar: Nov- Dec 1
| 5.6 | Notification of Award | bar: Nov- Dec 1 to Nov- Dec 3
| 5.7 | Signed contract | bar: Nov- Dec 4
| 5.8 | Contract Amendments | bar: Nov- Dec 4
| 5.9 | Contract completion | bar: Dec- Jan 1
| 5.1 | Contract Termination
8.5.1.19 | 6 | Procurement of Air cooling (AC) | No | 5 | 5 | 5 |  |  | DOA/ACIU
| 6.1 | Draft Request for Quotation | bar: Mar-Aprl 4 to Aprl-May 2
| 6.2 | Specific procurement Notice | bar: Aprl-May 3
| 6.3 | Invitation to Supplier/Contrator | bar: Aprl-May 3
| 6.4 | Receive Quotations | bar: Aprl-May 4 to May-June 4
| 6.5 | Comparision Quotations | bar: May-June 4
| 6.6 | Notification of Award | bar: May-June 4 to June-July 2
| 6.7 | Signed contract | bar: June-July 3
| 6.8 | Contract Amendments | bar: June-July 3
| 6.9 | Contract completion | bar: June-July 4
| 6.1 | Contract Termination
2.12.2.216 | 7 | Consulting Services for Agriculture Business Analyst (ABA) | No | 1 | 24 | 1 |  |  | DOA/ACIU/World Bank
| 7.1 | Terms of References | bar: Sep-Oct 1
| 7.2 | Invitation to identified/Selected Consultant | bar: Sep-Oct 2
| 7.3 | Draft Negotiated Contract | bar: Sep-Oct 3
| 7.4 | Standstill/Derifing | bar: Sep-Oct 4
| 7.5 | Notification of Award | bar: Sep-Oct 4
| 7.6 | Signed contract | bar: Oct-Nov 1
| 7.7 | Contract Amendments | bar: Oct-Nov 2 to June-July 4
| 7.8 | Contract completion | bar: June-July 4
| 7.9 | Contract Termination | bar: Oct-Nov 4; Nov- Dec 4; Dec- Jan 4; Feb- Mar 1; Feb- Mar 4; Mar-Aprl 4; Aprl-May 4; May-June 4; June-July 4
2.12.2.217 | 8 | Consulting Services for Agriculture Extension Specialist | No | 1 | 24 | 1 |  |  | DOA/ACIU/World Bank
| 8.1 | Terms of References | bar: Sep-Oct 1
| 8.2 | Invitation to identified/Selected Consultant | bar: Sep-Oct 2
| 8.3 | Draft Negotiated Contract | bar: Sep-Oct 3
| 8.4 | Standstill/Derifing | bar: Sep-Oct 4
| 8.5 | Notification of Award | bar: Sep-Oct 4
| 8.6 | Signed contract | bar: Oct-Nov 1
| 8.7 | Contract Amendments | bar: Oct-Nov 2 to June-July 4
| 8.8 | Contract completion | bar: June-July 4
| 8.9 | Contract Termination | bar: Oct-Nov 4; Nov- Dec 4; Dec- Jan 4; Jan-Feb 4; Feb- Mar 4; Mar-Aprl 4; Aprl-May 4; May-June 4; June-July 4
2.12.2.218 | 9 | Consulting Services for Technical Works (Junior Agriculture Technician) | No | 3 | 9 | 3 |  |  | DOA/ACIU
| 9.1 | Draft Request for Quotation | bar: Sep-Oct 3
| 9.2 | Specific procurement Notice | bar: Sep-Oct 4
| 9.3 | Invitation to Supplier/Contrator | bar: Oct-Nov 1
| 9.4 | Receive Quotations | bar: Oct-Nov 2
| 9.5 | Comparision Quotations | bar: Oct-Nov 2
| 9.6 | Notification of Award | bar: Oct-Nov 3
| 9.7 | Signed contract | bar: Oct-Nov 4
| 9.8 | Contract Amendments | bar: Nov- Dec 1 to June-July 3
| 9.9 | Contract completion | bar: June-July 4
| 9.1 | Contract Termination | bar: Oct-Nov 4; Nov- Dec 4; Dec- Jan 4; Jan-Feb 4; Feb- Mar 4; Mar-Aprl 4; Aprl-May 4; May-June 4; June-July 4
2.151.170.3 | 10 | Training on commercial agricultural production, processing and marketing | No | 50 | 25 | 10 | 20 | 20 | DOA/ACIU
| 10.1 | Justification for Direct Procurement | bar: Oct-Nov 3; Nov- Dec 3; Dec- Jan 3; Jan-Feb 3; Feb- Mar 3; Mar-Aprl 3; Aprl-May 3; May-June 3
| 10.2 | Invitation to Supplier/Contractor | bar: Oct-Nov 3; Nov- Dec 3; Dec- Jan 3; Jan-Feb 3; Feb- Mar 3; Mar-Aprl 3; Aprl-May 3; May-June 3
| 10.3 | Draft Contract | bar: Oct-Nov 4; Nov- Dec 4; Dec- Jan 4; Jan-Feb 4; Feb- Mar 4; Mar-Aprl 4; Aprl-May 4; May-June 4
| 10.4 | Notification Award | bar: Nov- Dec 1; Dec- Jan 1; Jan-Feb 1; Feb- Mar 1; Mar-Aprl 1; Aprl-May 1; May-June 1; June-July 1
| 10.5 | Signed contract | bar: Nov- Dec 1; Dec- Jan 1; Jan-Feb 1; Feb- Mar 1; Mar-Aprl 1; Aprl-May 1; May-June 1; June-July 1
| 10.6 | Contract Amendments | bar: Nov- Dec 2; Dec- Jan 2; Jan-Feb 2; Feb- Mar 2; Mar-Aprl 2; Aprl-May 2
| 10.7 | Contract completion | bar: Nov- Dec 3; Dec- Jan 3; Jan-Feb 3; Feb- Mar 3; Mar-Aprl 3; Aprl-May 2 to Aprl-May 3; May-June 2; June-July 2
| 10.8 | Contract Termination | bar: Nov- Dec 3; Dec- Jan 3; Jan-Feb 3; Feb- Mar 3; Mar-Aprl 3; Aprl-May 3; May-June 2; June-July 2 to June-July 3
2.151.170.2 | 11 | Training on commercial business plan development and implementation for seed producer co-operatives | No | 4 | 12 | 2 | 2 | 0 | DOA/ACIU
| 11.1 | Justification for Direct Procurement | bar: Oct-Nov 3; Nov- Dec 3; Dec- Jan 3; Jan-Feb 3; Feb- Mar 3; Mar-Aprl 3; Aprl-May 3; May-June 3
| 11.2 | Invitation to Supplier/Contractor | bar: Oct-Nov 3; Nov- Dec 3; Dec- Jan 3; Jan-Feb 3; Feb- Mar 3; Mar-Aprl 3; Aprl-May 3; May-June 3
| 11.3 | Draft Contract | bar: Oct-Nov 4; Nov- Dec 4; Dec- Jan 4; Jan-Feb 4; Feb- Mar 4; Mar-Aprl 4; Aprl-May 4; May-June 4
| 11.4 | Notification Award | bar: Nov- Dec 1; Dec- Jan 1; Jan-Feb 1; Feb- Mar 1; Mar-Aprl 1; Aprl-May 1; May-June 1; June-July 1
| 11.5 | Signed contract | bar: Nov- Dec 1; Dec- Jan 1; Jan-Feb 1; Feb- Mar 1; Mar-Aprl 1; Aprl-May 1; May-June 1; June-July 1
| 11.6 | Contract Amendments | bar: Nov- Dec 2; Dec- Jan 2; Jan-Feb 2; Feb- Mar 2; Mar-Aprl 2; Aprl-May 2
| 11.7 | Contract completion | bar: Nov- Dec 3; Dec- Jan 3; Jan-Feb 3; Feb- Mar 3; Mar-Aprl 3; Aprl-May 2 to Aprl-May 3; May-June 2; June-July 2
| 11.8 | Contract Termination | bar: Nov- Dec 3; Dec- Jan 3; Jan-Feb 3; Feb- Mar 3; Mar-Aprl 3; Aprl-May 3; May-June 2; June-July 2 to June-July 3
2.152.732 | 12 | Workshop on learning and innovation for farmers group, co-operatives, WUAs/WUCs , municipalities representatives and other concerned stakeholders | No | 3 | 18 | 1 | 1 | 1 | DOA/ACIU/World Bank
| 12.1 | Justification for Direct Procurement | bar: Oct-Nov 3; Jan-Feb 4; Aprl-May 2
| 12.2 | Invitation to Supplier/Contractor | bar: Oct-Nov 4; Feb- Mar 1; Aprl-May 3
| 12.3 | Draft Contract | bar: Oct-Nov 4; Feb- Mar 1; Aprl-May 3
| 12.4 | Notification Award | bar: Nov- Dec 1; Feb- Mar 2; Aprl-May 4
| 12.5 | Signed contract | bar: Nov- Dec 1; Feb- Mar 2; Aprl-May 4
| 12.6 | Contract Amendments | bar: Nov- Dec 2; Feb- Mar 3; May-June 1
| 12.7 | Contract completion | bar: Nov- Dec 2; Feb- Mar 3; May-June 1
| 12.8 | Contract Termination | bar: Nov- Dec 3; Feb- Mar 4; May-June 2
2.152.733 | 13 | Interaction workshop on ACIU project activities with concerned stakeholders | No | 6 | 9 | 2 | 2 | 2 | PIU/DOA/ACIU
| 13.1 | Justification for Direct Procurement | bar: Oct-Nov 1; Nov- Dec 2; Jan-Feb 3; Mar-Aprl 2; Aprl-May 4; May-June 4
| 13.2 | Invitation to Supplier/Contractor | bar: Oct-Nov 1; Nov- Dec 2; Jan-Feb 3; Mar-Aprl 2; Aprl-May 4; May-June 4
| 13.3 | Draft Contract | bar: Oct-Nov 2; Nov- Dec 3; Jan-Feb 4; Mar-Aprl 3; May-June 1; June-July 1
| 13.4 | Notification Award | bar: Oct-Nov 2; Nov- Dec 3; Jan-Feb 4; Mar-Aprl 3; May-June 1; June-July 1
| 13.5 | Signed contract | bar: Oct-Nov 3; Nov- Dec 4; Feb- Mar 1; Mar-Aprl 4; May-June 2; June-July 2
| 13.6 | Contract Amendments | bar: Oct-Nov 3; Nov- Dec 4; Feb- Mar 1; Mar-Aprl 4; May-June 2; June-July 2
| 13.7 | Contract completion | bar: Oct-Nov 4; Dec- Jan 1; Feb- Mar 2; Aprl-May 1; May-June 3; June-July 3
| 13.8 | Contract Termination | bar: Oct-Nov 4; Dec- Jan 1; Feb- Mar 2; Aprl-May 1; May-June 3; June-July 3
2.153.142.7 | 14 | Project implementation guideline and other agricultural technology booklets publication | No | 12 | 12 | 4 | 4 | 4 | DOA/ACIU
| 14.1 | Justification for Direct Procurement | bar: Sep-Oct 1
| 14.2 | Invitation to Supplier/Contractor | bar: Sep-Oct 3
| 14.3 | Draft Contract | bar: Sep-Oct 4
| 14.4 | Notification Award | bar: Oct-Nov 2
| 14.5 | Signed contract | bar: Oct-Nov 2
| 14.6 | Contract Amendments | bar: Oct-Nov 3 to Mar-Aprl 2
| 14.7 | Contract completion | bar: Mar-Aprl 2 to June-July 3
| 14.8 | Contract Termination | bar: June-July 4
2.153.142.5 | 15 | Production and of video docummentry on agricultue technology demonstration | No | 3 | 12 | 1 | 1 | 1 | DOA/ACIU
| 15.1 | Draft Request for Quotation | bar: Sep-Oct 2
| 15.2 | Specific procurement Notice | bar: Sep-Oct 3
| 15.3 | Invitation to Supplier/Contrator | bar: Oct-Nov 3
| 15.4 | Receive Quotations | bar: Oct-Nov 4
| 15.5 | Comparision Quotations | bar: Nov- Dec 1
| 15.6 | Notification of Award | bar: Nov- Dec 2
| 15.7 | Signed contract | bar: Nov- Dec 3
| 15.8 | Contract Amendments | bar: Nov- Dec 3 to Jan-Feb 3; Mar-Aprl 1 to May-June 1
| 15.9 | Contract completion | bar: Jan-Feb 3 to Feb- Mar 3; May-June 1 to June-July 3
| 15.1 | Contract Termination | bar: Feb- Mar 4; June-July 4
2.15.13.401 | 16 | Cereal crop based technology demonstration in block | No | 173 | 26.29 | 60 | 60 | 53 | DOA/ACIU/WUAs
| 16.1 | Request Notice for proposal Submission from Individual farmers/Group/Cooperatives/WUAs | bar: Sep-Oct 1
| 16.2 | Receive Request Proposal | bar: Sep-Oct 1 to Sep-Oct 4
| 16.3 | Primary field verification | bar: Oct-Nov 1 to Oct-Nov 2
| 16.4 | Selection of farmer, farmer group or cooperatives by Granst Support Selection Committee | bar: Oct-Nov 3
| 16.5 | Draft Request for Quotation | bar: Oct-Nov 3
| 16.6 | Specific Procurement Notice | bar: Oct-Nov 4
| 16.7 | Invitation to Supplier/Contractor | bar: Oct-Nov 4
| 16.8 | Amendements to Request for Quotations | bar: Nov- Dec 1
| 16.9 | Receive Quotattions | bar: Nov- Dec 2
| 16.1 | Noticification of Award | bar: Nov- Dec 3
| 16.11 | Signed contract | bar: Nov- Dec 3
| 16.12 | Contract Amendments | bar: Nov- Dec 3 to Dec- Jan 3; Feb- Mar 1 to May-June 2
| 16.13 | Contract completion | bar: Dec- Jan 4 to Jan-Feb 3; Mar-Aprl 3; May-June 3 to June-July 3
| 16.14 | Contract Termination | bar: Jan-Feb 3 to Jan-Feb 4; Mar-Aprl 3 to Mar-Aprl 4; June-July 3 to June-July 4
2.15.13.402 | 17 | Cereal seed multiplication | Ha | 400 | 50 | 250 | 0 | 150 | DOA/ACIU/WUAs
| 17.1 | Request Notice for proposal Submission from Individual farmers/Group/Cooperatives/WUAs | bar: Agu-Sep 2; Mar-Aprl 1
| 17.2 | Receive Request Proposal | bar: Agu-Sep 3 to Sep-Oct 2; Mar-Aprl 2 to Aprl-May 1
| 17.3 | Primary field verification | bar: Sep-Oct 3; Aprl-May 2 to Aprl-May 3
| 17.4 | Selection of farmer, farmer group or cooperatives by Granst Support Selection Committee | bar: Sep-Oct 3; Aprl-May 4
| 17.5 | Draft Request for Quotation | bar: Sep-Oct 4; Aprl-May 4
| 17.6 | Specific Procurement Notice | bar: Sep-Oct 4; Aprl-May 4
| 17.7 | Invitation to Supplier/Contractor | bar: Sep-Oct 4; Aprl-May 4
| 17.8 | Amendements to Request for Quotations | bar: Sep-Oct 4; Aprl-May 4
| 17.9 | Receive Quotattions | bar: Oct-Nov 1; May-June 1
| 17.1 | Noticification of Award | bar: Oct-Nov 1; May-June 1
| 17.11 | Signed contract | bar: Oct-Nov 1; May-June 1
| 17.12 | Contract Amendments | bar: Oct-Nov 2 to Nov- Dec 4; May-June 2 to June-July 3
| 17.13 | Contract completion | bar: Dec- Jan 1 to Jan-Feb 4; June-July 4
| 17.14 | Contract Termination | bar: Jan-Feb 4; June-July 4
2.15.14.387 | 18 | Fruit orchard demonstration in block | Ha | 127 | 80.01 | 10 | 10 | 107 | DOA/ACIU/WUAs
| 18.1 | Request Notice for proposal Submission from Individual farmers/Group/Cooperatives/WUAs | bar: Agu-Sep 2; Nov- Dec 4; Mar-Aprl 1
| 18.2 | Receive Request Proposal | bar: Agu-Sep 3 to Sep-Oct 2; Dec- Jan 1 to Dec- Jan 4; Mar-Aprl 2 to Aprl-May 1
| 18.3 | Primary field verification | bar: Sep-Oct 3 to Sep-Oct 4; Jan-Feb 1 to Jan-Feb 2; Aprl-May 2 to Aprl-May 3
| 18.4 | Selection of farmer, farmer group or cooperatives by Granst Support Selection Committee | bar: Oct-Nov 1; Jan-Feb 3; Aprl-May 4
| 18.5 | Draft Request for Quotation | bar: Oct-Nov 2; Jan-Feb 4; May-June 1
| 18.6 | Specific procurement Notice | bar: Oct-Nov 2; Jan-Feb 4; May-June 1
| 18.7 | Invitation to Supplier/Contrator | bar: Oct-Nov 3; Feb- Mar 1; May-June 2
| 18.8 | Receive Quotations | bar: Oct-Nov 3; Feb- Mar 1; May-June 2
| 18.9 | Comparision Quotations | bar: Oct-Nov 3; Feb- Mar 1; May-June 3
| 18.1 | Notification of Award | bar: Oct-Nov 4; Feb- Mar 2; May-June 3
| 18.11 | Signed contract | bar: Oct-Nov 4; Feb- Mar 2; May-June 3
| 18.12 | Contract Amendments | bar: Nov- Dec 1 to Dec- Jan 3; Feb- Mar 3 to Mar-Aprl 4; May-June 4 to June-July 3
| 18.13 | Contract completion | bar: Dec- Jan 4 to Feb- Mar 1; Aprl-May 1 to Aprl-May 4; June-July 4
| 18.14 | Contract Termination | bar: Feb- Mar 2; May-June 1; June-July 4
2.15.15.371 | 19 | Vegetable production demonstration in block | Ha | 190 | 66.5 | 90 | 60 | 40 | DOA/ACIU/WUAs
| 19.1 | Request Notice for proposal Submission from Individual farmers/Group/Cooperatives/WUAs | bar: Agu-Sep 2
| 19.2 | Receive Request Proposal | bar: Agu-Sep 3 to Sep-Oct 2
| 19.3 | Primary field verification | bar: Sep-Oct 3 to Sep-Oct 4
| 19.4 | Selection of farmer, farmer group or cooperatives by Granst Support Selection Committee | bar: Sep-Oct 4
| 19.5 | Draft Request for Quotation | bar: Sep-Oct 4
| 19.6 | Specific procurement Notice | bar: Sep-Oct 4
| 19.7 | Invitation to Supplier/Contrator | bar: Sep-Oct 4
| 19.8 | Receive Quotations | bar: Sep-Oct 4
| 19.9 | Comparision Quotations | bar: Sep-Oct 4
| 19.1 | Notification of Award | bar: Sep-Oct 4
| 19.11 | Signed contract | bar: Oct-Nov 1
| 19.12 | Contract Amendments | bar: Oct-Nov 2 to Dec- Jan 2; Feb- Mar 2 to May-June 1
| 19.13 | Contract completion | bar: Dec- Jan 2 to Jan-Feb 4; Mar-Aprl 4; May-June 2 to June-July 3
| 19.14 | Contract Termination | bar: Feb- Mar 1; Aprl-May 1; June-July 4
2.15.16.172 | 20 | Vegetable seed production program | Ha | 30 | 30 | 15 | 10 | 5 | DOA/ACIU/WUAs
| 20.1 | Request Notice for proposal Submission from Individual farmers/Group/Cooperatives/WUAs | bar: Agu-Sep 3
| 20.2 | Receive Request Proposal | bar: Agu-Sep 4 to Sep-Oct 3
| 20.3 | Primary field verification | bar: Sep-Oct 4 to Oct-Nov 1
| 20.4 | Selection of farmer, farmer group or cooperatives by Granst Support Selection Committee | bar: Oct-Nov 2
| 20.5 | Draft Request for Quotation | bar: Oct-Nov 3
| 20.6 | Specific procurement Notice | bar: Oct-Nov 3
| 20.7 | Invitation to Supplier/Contrator | bar: Oct-Nov 4
| 20.8 | Receive Quotations | bar: Oct-Nov 4
| 20.9 | Comparision Quotations | bar: Oct-Nov 4
| 20.1 | Notification of Award | bar: Nov- Dec 1
| 20.11 | Signed contract | bar: Nov- Dec 1
| 20.12 | Contract Amendments | bar: Nov- Dec 2 to Dec- Jan 3; Feb- Mar 2 to May-June 1
| 20.13 | Contract completion | bar: Dec- Jan 4 to Jan-Feb 4; May-June 2 to June-July 3
| 20.14 | Contract Termination | bar: Feb- Mar 1; June-July 4
2.15.16.173 | 21 | FFS Conduction and Follow up | [6 empty] | DOA/ACIU/WUAs/Municipalities
| 21.1 | Planning for conduction of FFS (crop, variety, seed, materials) | No | 20 | 20 | 5 | 9 | 6
| 21.2 | Pre preparation meeting two times with municipalities local leader, WUAs/WUCs & field staff), famer selection & organize in group | bar: Sep-Oct 1; Sep-Oct 3; Dec- Jan 4; Jan-Feb 2; Mar-Aprl 2; Mar-Aprl 4
| 21.3 | Select personnel to conduct program | bar: Sep-Oct 4; Jan-Feb 3; Aprl-May 1
| 21.4 | Agrement to the farmer group and FFS conduct | bar: Oct-Nov 1; Feb- Mar 1; Aprl-May 2
| 21.5 | Technical backstopping support to faciltators in crop FFS at orientation meeting | bar: Oct-Nov 2 to Jan-Feb 4; Feb- Mar 2 to June-July 4
| 21.6 | Field visit by stakeholder or Farmers Day | bar: Jan-Feb 4; Aprl-May 4; June-July 4
| 21.7 | Reporting | bar: Feb- Mar 1; May-June 1; June-July 4
2.15.16.174 | 22 | Construciton and Implementation of mini plant protection laboratory | No | 1 | 10 | 1 |  |  | DOA/ACIU/WUAs
| 22.1 | Draft Request for Quotation | bar: Agu-Sep 3
| 22.2 | Specific procurement Notice | bar: Agu-Sep 4
| 22.3 | Invitation to Supplier/Contrator | bar: Agu-Sep 4
| 22.4 | Receive Quotations | bar: Sep-Oct 1
| 22.5 | Comparision Quotations | bar: Sep-Oct 2
| 22.6 | Notification of Award | bar: Sep-Oct 3
| 22.7 | Signed contract | bar: Sep-Oct 3
| 22.8 | Contract Amendments | bar: Sep-Oct 4 to Nov- Dec 3
| 22.9 | Contract completion | bar: Nov- Dec 4 to Jan-Feb 1
| 22.1 | Contract Termination | bar: Jan-Feb 2
2.15.16.175 | 23 | Plant protection services on farmers demand | No | 10 | 10 | 3 | 4 | 3 | DOA/ACIU/WUAs
| 23.1 | Justification for Direct Procurement | bar: Agu-Sep 4
| 23.2 | Invitation to Supplier/Contractor | bar: Sep-Oct 1
| 23.3 | Draft Contract | bar: Sep-Oct 2
| 23.4 | Notification Award | bar: Sep-Oct 3
| 23.5 | Signed contract | bar: Sep-Oct 3; June-July 4
| 23.6 | Contract Amendments | bar: Nov- Dec 1 to Nov- Dec 2; Dec- Jan 4 to Jan-Feb 1; Feb- Mar 4 to Mar-Aprl 1; May-June 4 to June-July 1; June-July 4
| 23.7 | Contract completion | bar: Nov- Dec 3; Jan-Feb 2; Mar-Aprl 2; June-July 4
| 23.8 | Contract Termination | bar: Nov- Dec 4; Jan-Feb 3; Mar-Aprl 3; June-July 4
2.15.16.176 | 24 | Soil testing and management compangain | No | 15 | 15 | 5 | 5 | 5 | DOA/ACIU/WUAs
| 24.1 | Draft Request for Quotation | bar: Sep-Oct 4
| 24.2 | Specific procurement Notice | bar: Oct-Nov 1 to Oct-Nov 2
| 24.3 | Invitation to Supplier/Contrator | bar: Oct-Nov 3
| 24.4 | Receive Quotations | bar: Oct-Nov 4
| 24.5 | Comparision Quotations | bar: Oct-Nov 4
| 24.6 | Notification of Award | bar: Nov- Dec 1
| 24.7 | Signed contract | bar: Nov- Dec 1
| 24.8 | Contract Amendments | bar: Nov- Dec 2 to Nov- Dec 3; Jan-Feb 4 to Feb- Mar 1; Mar-Aprl 4 to Aprl-May 1
| 24.9 | Contract completion | bar: Nov- Dec 4; Feb- Mar 2; Aprl-May 2
| 24.1 | Contract Termination | bar: Dec- Jan 1; Feb- Mar 3; Aprl-May 3
2.15.20.493 | 25 | Livestock Production Support | No | 50 | 80 | 15 | 20 | 15 | DOA/ACIU/WUAs/Municipalities
| 25.1 | Request Notice for proposal Submission from Individual farmers/Group/Cooperatives/WUAs | bar: Oct-Nov 2
| 25.2 | Receive Request Proposal | bar: Oct-Nov 3 to Nov- Dec 2
| 25.3 | Primary field verification | bar: Nov- Dec 3 to Nov- Dec 4
| 25.4 | Selection of farmer, farmer group or cooperatives by Granst Support Selection Committee | bar: Dec- Jan 1
| 25.5 | Draft Request for Quotation | bar: Dec- Jan 2
| 25.6 | Specific Procurement Notice | bar: Dec- Jan 2
| 25.7 | Invitation to Supplier/Contractor | bar: Dec- Jan 3
| 25.8 | Amendements to Request for Quotations | bar: Dec- Jan 4
| 25.9 | Receive Quotattions | bar: Dec- Jan 4
| 25.1 | Noticification of Award | bar: Jan-Feb 1
| 25.11 | Signed contract | bar: Jan-Feb 1
| 25.12 | Contract Amendments | bar: Jan-Feb 2 to Aprl-May 2
| 25.13 | Contract completion | bar: Aprl-May 2 to June-July 3
| 25.14 | Contract Termination | bar: June-July 4
2.15.20.494 | 26 | Forage production and processing for livestock production | No | 10 | 15 | 3 | 4 | 3 | DOA/ACIU/WUAs/Municipalities
| 26.1 | Request Notice for proposal Submission from Individual farmers/Group/Cooperatives/WUAs | bar: Oct-Nov 2
| 26.2 | Receive Request Proposal | bar: Oct-Nov 3 to Nov- Dec 2
| 26.3 | Primary field verification | bar: Nov- Dec 3 to Nov- Dec 4
| 26.4 | Selection of farmer, farmer group or cooperatives by Granst Support Selection Committee | bar: Dec- Jan 1
| 26.5 | Draft Request for Quotation | bar: Dec- Jan 2
| 26.6 | Specific Procurement Notice | bar: Dec- Jan 2
| 26.7 | Invitation to Supplier/Contractor | bar: Dec- Jan 3
| 26.8 | Amendements to Request for Quotations | bar: Dec- Jan 4
| 26.9 | Receive Quotattions | bar: Dec- Jan 4
| 26.1 | Noticification of Award | bar: Jan-Feb 1
| 26.11 | Signed contract | bar: Jan-Feb 1
| 26.12 | Contract Amendments | bar: Jan-Feb 2 to Aprl-May 2
| 26.13 | Contract completion | bar: Aprl-May 2 to June-July 3
| 26.14 | Contract Termination | bar: June-July 4
2.15.20.495 | 27 | Breed improvement and disease management | No | 15 | 15 | 5 | 5 | 5 | DOA/ACIU/WUAs/Municipalities
| 27.1 | Justification for Direct Procurement | bar: Oct-Nov 1
| 27.2 | Invitation to Supplier/Contractor | bar: Oct-Nov 2 to Oct-Nov 3
| 27.3 | Draft Contract | bar: Oct-Nov 3
| 27.4 | Notification Award | bar: Oct-Nov 4
| 27.5 | Signed contract | bar: Nov- Dec 1
| 27.6 | Contract Amendments | bar: Nov- Dec 2 to Jan-Feb 3; Mar-Aprl 1 to May-June 2
| 27.7 | Contract completion | bar: Jan-Feb 3 to Feb- Mar 3; May-June 2 to June-July 3
| 27.8 | Contract Termination | bar: Feb- Mar 4; June-July 4
2.191.1106 | 28 | Field program monitoring and evaluation | No | 50 | 9 | 10 | 20 | 20 | DOA/ACIU/WUAs/Municipalities
| 28.1 | During program implementation /completion stage | bar: Agu-Sep 4 to June-July 4
2.19.2.711 | 29 | Expenses for project activitie review meeting | No | 12 | 12 | 12 | 12 | 12 | DOA/ACIU/WUAs/Municipalities
| 29.1 | Quarterly | bar: Nov- Dec 1; Mar-Aprl 1; June-July 4
2.110.1857 | 30 | Support on Hi-tech nursury establishment | No | 3 | 9 | 1 | 1 | 1 | DOA/ACIU/WUAs/Municipalities
| 30.1 | Request Notice for proposal Submission from Individual farmers/Group/Cooperatives/WUAs | bar: Sep-Oct 1
| 30.2 | Receive Request Proposal | bar: Sep-Oct 2 to Oct-Nov 1
| 30.3 | Primary field verification | bar: Oct-Nov 2 to Oct-Nov 3
| 30.4 | Selection of farmer, farmer group or cooperatives by Granst Support Selection Committee | bar: Oct-Nov 4 to Nov- Dec 1
| 30.5 | Draft Request for Quotation | bar: Nov- Dec 2
| 30.6 | Specific Procurement Notice | bar: Nov- Dec 3
| 30.7 | Invitation to Supplier/Contractor | bar: Nov- Dec 3
| 30.8 | Amendements to Request for Quotations | bar: Nov- Dec 4
| 30.9 | Receive Quotattions | bar: Nov- Dec 4
| 30.1 | Noticification of Award | bar: Nov- Dec 4
| 30.11 | Signed contract | bar: Dec- Jan 1
| 30.12 | Contract Amendments | bar: Dec- Jan 2 to Jan-Feb 3; Mar-Aprl 1 to Aprl-May 4
| 30.13 | Contract completion | bar: Jan-Feb 4 to Feb- Mar 4; May-June 1 to June-July 3
| 30.14 | Contract Termination | bar: Mar-Aprl 1; June-July 4
5.110.1858 | 31 | Demand base agricultural production support | No | 70 | 70 | 20 | 20 | 30 | DOA/ACIU/WUAs/Municipalities
| 31.1 | Request Notice for proposal Submission from flood affected farmers | bar: Sep-Oct 2
| 31.2 | Receive Request Proposal | bar: Sep-Oct 3 to Oct-Nov 2
| 31.3 | Primary field verification | bar: Oct-Nov 3 to Oct-Nov 4; Feb- Mar 2 to Feb- Mar 3
| 31.4 | Selection of farmer, farmer group or cooperatives by Granst Support Selection Committee | bar: Nov- Dec 1
| 31.5 | Noticification of Award | bar: Nov- Dec 1
| 31.6 | Signed contract | bar: Nov- Dec 1
| 31.7 | Contract Amendments | bar: Nov- Dec 1 to Dec- Jan 3; Feb- Mar 4 to Aprl-May 3
| 31.8 | Contract completion | bar: Dec- Jan 4 to Jan-Feb 4; Aprl-May 4 to June-July 3
| 31.9 | Contract Termination | bar: Feb- Mar 1; June-July 4
5.1.10.1859 | 32 | Commercial vegetable production in Agri-Nets | No | 15 | 45 | 5 | 5 | 5 | DOA/ACIU/WUAs/Municipalities
| 32.1 | Request Notice for proposal Submission from Individual farmers/Group/Cooperatives/WUAs | bar: Agu-Sep 3
| 32.2 | Receive Request Proposal | bar: Agu-Sep 4 to Sep-Oct 3
| 32.3 | Primary field verification | bar: Sep-Oct 4 to Oct-Nov 2
| 32.4 | Selection of farmer, farmer group or cooperatives by Granst Support Selection Committee | bar: Oct-Nov 3
| 32.5 | Draft Request for Quotation | bar: Oct-Nov 4
| 32.6 | Specific Procurement Notice | bar: Nov- Dec 1
| 32.7 | Invitation to Supplier/Contractor | bar: Nov- Dec 2
| 32.8 | Amendements to Request for Quotations | bar: Nov- Dec 3
| 32.9 | Receive Quotattions | bar: Nov- Dec 4
| 32.1 | Noticification of Award | bar: Dec- Jan 1
| 32.11 | Signed contract | bar: Dec- Jan 2
| 32.12 | Contract Amendments | bar: Dec- Jan 3 to Feb- Mar 1; Mar-Aprl 2 to May-June 3
| 32.13 | Contract completion | bar: Feb- Mar 1 to Mar-Aprl 1; May-June 3 to June-July 3
| 32.14 | Contract Termination | bar: Mar-Aprl 2; June-July 4
5.1.10.1860 | 33 | Marginalized, poor and landless specific demonstration and support | No | 150 | 30 | 50 | 50 | 50 | DOA/ACIU/WUAs/Municipalities
| 33.1 | Request Notice for proposal Submission from flood affected farmers | bar: Sep-Oct 2
| 33.2 | Receive Request Proposal | bar: Sep-Oct 3 to Oct-Nov 2
| 33.3 | Primary field verification | bar: Oct-Nov 3 to Oct-Nov 4; Feb- Mar 2 to Feb- Mar 3
| 33.4 | Selection of farmer, farmer group or cooperatives by Granst Support Selection Committee | bar: Nov- Dec 1
| 33.5 | Noticification of Award | bar: Nov- Dec 1
| 33.6 | Signed contract | bar: Nov- Dec 1
| 33.7 | Contract Amendments | bar: Nov- Dec 1 to Dec- Jan 2; Feb- Mar 4 to Aprl-May 2
| 33.8 | Contract completion | bar: Dec- Jan 3 to Jan-Feb 4; Aprl-May 3 to June-July 3
| 33.9 | Contract Termination | bar: Feb- Mar 1; June-July 4
5.1.10.1861 | 34 | Special agricultural production support in flood affected area | Ha | 100 | 50 | 10 | 45 | 45 | DOA/ACIU/WUAs/Municipalities
| 34.1 | Request Notice for proposal Submission from flood affected farmers | bar: Agu-Sep 3
| 34.2 | Receive Request Proposal | bar: Agu-Sep 4 to Sep-Oct 3; Oct-Nov 4 to Nov- Dec 3; Feb- Mar 2 to Mar-Aprl 1
| 34.3 | Primary field verification | bar: Sep-Oct 4; Nov- Dec 4; Mar-Aprl 2
| 34.4 | Selection of farmer, farmer group or cooperatives by Granst Support Selection Committee | bar: Oct-Nov 1; Dec- Jan 1; Mar-Aprl 3
| 34.5 | Draft Request for Quotation | bar: Oct-Nov 1; Dec- Jan 1; Mar-Aprl 3
| 34.6 | Specific Procurement Notice | bar: Oct-Nov 1; Dec- Jan 1; Mar-Aprl 3
| 34.7 | Invitation to Supplier/Contractor | bar: Oct-Nov 1; Dec- Jan 1; Mar-Aprl 3
| 34.8 | Amendements to Request for Quotations | bar: Oct-Nov 2; Dec- Jan 2; Mar-Aprl 4
| 34.9 | Receive Quotattions | bar: Oct-Nov 2; Dec- Jan 2; Mar-Aprl 4
| 34.1 | Noticification of Award | bar: Oct-Nov 2; Dec- Jan 2; Mar-Aprl 4
| 34.11 | Signed contract | bar: Oct-Nov 2; Dec- Jan 2; Mar-Aprl 4
| 34.12 | Contract Amendments | bar: Oct-Nov 3 to Dec- Jan 4; Feb- Mar 3 to May-June 2
| 34.13 | Contract completion | bar: Dec- Jan 4 to Feb- Mar 2; May-June 3 to June-July 4
| 34.14 | Contract Termination | bar: Feb- Mar 2; June-July 4
5.1.10.1862 | 35 | Competitive research and grant support for agricultural production demonstration | No | 50 | 50 | 10 | 20 | 20 | DOA/ACIU/WUAs/Municipalities
| 35.1 | Justification for Direct Procurement | bar: Oct-Nov 3
| 35.2 | Invitation to Supplier/Contractor | bar: Oct-Nov 4
| 35.3 | Draft Contract | bar: Oct-Nov 4
| 35.4 | Notification Award | bar: Nov- Dec 1
| 35.5 | Signed contract | bar: Nov- Dec 2
| 35.6 | Contract Amendments | bar: Nov- Dec 3 to Jan-Feb 2; Mar-Aprl 2 to May-June 2
| 35.7 | Contract completion | bar: Jan-Feb 3 to Feb- Mar 4; May-June 3 to June-July 3
| 35.8 | Contract Termination | bar: Feb- Mar 4; June-July 4
8.5.4.647 | 36 | Seed storage facilities support for seed producers co-operatives | No | 2 | 50 |  | 1 | 1 | DOA/ACIU/WUAs/Municipalities
| 36.1 | Request Notice for proposal Submission from Seed Cooperatives | bar: Nov- Dec 2
| 36.2 | Receive Request Proposal | bar: Nov- Dec 3 to Dec- Jan 2
| 36.3 | Primary field verification | bar: Dec- Jan 3 to Dec- Jan 4
| 36.4 | Selection of farmer, farmer group or cooperatives by Granst Support Selection Committee | bar: Jan-Feb 1
| 36.5 | Draft Bidding Documents (RFB) | bar: Jan-Feb 2 to Jan-Feb 3
| 36.6 | Specific procurement Notice | bar: Jan-Feb 4
| 36.7 | Amendments to Bidding Documents | bar: Feb- Mar 1
| 36.8 | Technical Bid Submission/Opening/minutes | bar: Feb- Mar 2
| 36.9 | Evaluation of Technical proposal | bar: Feb- Mar 3
| 36.1 | Opening of Financial proposal/minutes | bar: Feb- Mar 4
| 36.11 | Bid validity Extension | bar: Feb- Mar 4
| 36.12 | Bid Evaluation Report and Recommendation for Awar | bar: Feb- Mar 4
| 36.13 | Standstill/Derifing | bar: Mar-Aprl 1
| 36.14 | Notification of Award | bar: Mar-Aprl 1
| 36.15 | Signed contract | bar: Mar-Aprl 2 to May-June 2
| 36.16 | Contract Amendments | bar: May-June 2 to June-July 3
| 36.17 | Contract completion | bar: June-July 3 to June-July 4
| 36.18 | Contract Termination | bar: May-June 2 to June-July 3
8.5.4.648 | 37 | Banana ripening chamber support for banana producers | No | 2 | 200 |  | 1 | 1 | DOA/ACIU/WUAs/Municipalities
| 37.1 | Request Notice for proposal Submission from Individual farmers/Group/Cooperatives/WUAs | bar: Oct-Nov 1
| 37.2 | Receive Request Proposal | bar: May-June 2 to June-July 3
| 37.3 | Primary field verification | bar: May-June 2 to June-July 3
| 37.4 | Selection of farmer, farmer group or cooperatives by Granst Support Selection Committee | bar: Nov- Dec 4
| 37.5 | Draft Bidding Documents (RFB) | bar: Nov- Dec 4
| 37.6 | Specific procurement Notice | bar: May-June 2 to June-July 3
| 37.7 | Amendments to Bidding Documents | bar: May-June 2 to June-July 3
| 37.8 | Technical Bid Submission/Opening/minutes | bar: May-June 2 to June-July 3
| 37.9 | Evaluation of Technical proposal | bar: May-June 2 to June-July 3
| 37.1 | Opening of Financial proposal/minutes | bar: May-June 2 to June-July 3
| 37.11 | Bid validity Extension | bar: May-June 2 to June-July 3
| 37.12 | Bid Evaluation Report and Recommendation for Awar | bar: Jan-Feb 1
| 37.13 | Standstill/Derifing | bar: May-June 2 to June-July 3
| 37.14 | Notification of Award | bar: May-June 2 to June-July 3
| 37.15 | Signed contract | bar: May-June 2 to June-July 3
| 37.16 | Contract Amendments | bar: May-June 2 to June-July 3
| 37.17 | Contract completion | bar: May-June 2 to June-July 3
| 37.18 | Contract Termination | bar: May-June 2 to June-July 3
8.5.4.649 | 38 | Agricultural mechanization support | Sets | 100 | 300 | 33 | 33 | 34 | DOA/ACIU/WUAs/Municipalities
| 38.1 | Request Notice for proposal Submission from Individual farmers/Group/Cooperatives/WUAs | bar: Sep-Oct 2 to Oct-Nov 1
| 38.2 | Receive Request Proposal | bar: May-June 2 to June-July 3
| 38.3 | Primary field verification | bar: May-June 2 to June-July 3
| 38.4 | Selection of farmer, farmer group or cooperatives by Granst Support Selection Committee | bar: Nov- Dec 1
| 38.5 | Draft Request for Quotation | bar: May-June 2 to June-July 3
| 38.6 | Specific Procurement Notice | bar: Nov- Dec 2
| 38.7 | Invitation to Supplier/Contractor | bar: Nov- Dec 2
| 38.8 | Amendements to Request for Quotations | bar: Nov- Dec 2
| 38.9 | Receive Quotattions | bar: Nov- Dec 2 to Nov- Dec 3
| 38.1 | Noticification of Award | bar: Nov- Dec 3
| 38.11 | Signed contract | bar: Nov- Dec 3
| 38.12 | Contract Amendments | bar: Nov- Dec 4 to Feb- Mar 1
| 38.13 | Contract completion | bar: Feb- Mar 1 to Mar-Aprl 4
| 38.14 | Contract Termination | bar: Aprl-May 1 to Aprl-May 3
Additional Activities Action Plan
| 1 | Procurement of 4WD Pick Up | No | 2 | 200 |  |  |  | DOA/ACIU
| 1.1 | Draft Pre-qualification/Initial selection Documents | bar: Sep-Oct 2 to Oct-Nov 1
| 1.2 | Specific procurement Notice | bar: Oct-Nov 2 to Nov- Dec 1
| 1.3 | Amendments to Pre qualification/ Initial selection doc | bar: Nov- Dec 2
| 1.4 | Opening/minutes of Pre qualification/Initial selection | bar: Nov- Dec 3
| 1.5 | Pre qualification/Initial selection Evaluation Report | bar: Nov- Dec 4
| 1.6 | Draft Bidding Documents | bar: Nov- Dec 4
| 1.7 | Amendments to Bidding Documents | bar: Dec- Jan 1 to Dec- Jan 2
| 1.8 | Bid Submission/Opening/minutes | bar: Dec- Jan 2 to Dec- Jan 3
| 1.9 | Bid validity Extension | bar: Dec- Jan 4
| 1.1 | Bid Evaluation Report and Recommendation for Award | bar: Jan-Feb 1
| 1.11 | Standstill/Derifing | bar: Jan-Feb 2
| 1.12 | Notification of Award | bar: Jan-Feb 4
| 1.13 | Signed contract | bar: Feb- Mar 1
| 1.14 | Contract Amendments | bar: Feb- Mar 2 to Mar-Aprl 2
| 1.15 | Contract completion | bar: Mar-Aprl 3 to Mar-Aprl 4
| 1.16 | Contract Termination | bar: Aprl-May 1
| 2 | Consulting Services for Procurement Specialist | No | 1 | 45 |  |  |  | DOA/ACIU
| 2.1 | Terms of References | bar: Sep-Oct 1
| 2.2 | Invitation to identified/Selected Consultant | bar: Sep-Oct 2
| 2.3 | Draft Negotiated Contract | bar: Sep-Oct 3
| 2.4 | Standstill/Derifing | bar: Sep-Oct 4
| 2.5 | Notification of Award | bar: Sep-Oct 4
| 2.6 | Signed contract | bar: Oct-Nov 1
| 2.7 | Contract Amendments | bar: Oct-Nov 2
| 2.8 | Contract completion | bar: Oct-Nov 3 to June-July 4
| 2.9 | Contract Termination | bar: June-July 4